## Project schedule
| CIS-K ValiData Project | [6 empty] | Project start: | [7 empty] | 2025-09-01
| CIP NAME | Project lead | [5 empty] | Display week: | [7 empty] | 1
| https://ciskenya.co.ke/ | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20
| TASK | ASSIGNED TO | PROGRESS | START | DAYS | END | time axis 2025-09-01 to 2025-10-26
 | time axis 2025-09-01 to 2025-10-26
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Initiation |  | 0%
| Assign internal project sponsor |  | 0% | 2025-09-01 | 1 | 2025-09-01 | 1
| Establish internal project team |  | 0% | 2025-09-02 | 2 | 2025-09-03 | 2
| Review project charter and materials, and sign-off requisite documents |  | 0% | 2025-09-04 | 1 | 2025-09-04 | 1
| Formally communicate to CIS K readiness to progress |  | 0% | 2025-09-05 | 1 | 2025-09-05 | 1
| Planning and Setup |  | 0%
| Download and Deploy ValiData tool |  | 0% | 2025-09-08 | 2 | 2025-09-09 | 2
| Request tool activation from CISK |  | 0% | 2025-09-09 | 1 | 2025-09-09 | 1
| Configure CIP users and access rights |  | 0% | 2025-09-10 | 1 | 2025-09-10 | 1
| Request API from the CRBS |  | 0% | 2025-09-10 | 1 | 2025-09-10 | 1
| Perform API connectivity test |  | 0% | 2025-09-11 | 1 | 2025-09-11
| Attend UAT onboarding and training |  | 0% | 2025-09-12 | 1 | 2025-09-12 | 1
| Execution |  | 0%
| Prepare and upload credit data files |  | 0% | 2025-09-15 | 1 | 2025-09-15 | 1
| Review validation results |  | 0% | 2025-09-15 | 1 | 2025-09-15 | 1
| Resolve flagged errors and re-upload files |  | 0% | 2025-09-15 | 3 | 2025-09-17 | 3
| Submit validated files to CRBs |  | 0% | 2025-09-18 | 1 | 2025-09-18 | 1
| Review of submitted files for completeness by CRB |  | 0% | 2025-09-19 | 1 | 2025-09-19 | 1
| Monitoring |  | 0%
| Monitor feedback on validation, submission or error logs |  | 0% | 2025-09-15 | 3 | 2025-09-17 | 3
| Log any issues encountered |  | 0% | 2025-09-15 | 3 | 2025-09-17 | 3
| Feedback and Closure |  | 0% | 2025-09-17 | 2 | 2025-09-18 | 2
| Conduct a UAT review session |  | 0% | 2025-09-19 | 1 | 2025-09-19 | 1
| Submit final feedback to CISK |  | 0% | 2025-09-19 | 1 | 2025-09-19 | 1
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]
Note on R1: CIS Kenya: Insert Start Date